AI Compliance System Launch Plan (Powered by Addiction Rescue Inc.) Title: Building the First Fully AI-Powered DHCS Licensing, Certification, MAT/ASAM Readiness, and Joint Commission Compliance & Survey Submission Platform. This platform will be branded as: AI AGENT CLG (Compliance and Licensing Group – “CLG”) A rebranded evolution of the original “CLARA” concept, with unique distinction and less risk of trademark conflict.techandmedialaw.com STEP ONE – Legal Foundation & Ownership Structure Objective: Position Addiction Rescue Inc. as the founding nonprofit behind AI AGENT CLG, enabling access to mission-aligned funding and dual nonprofit–commercial growth. Key Actions:

- Confirm nonprofit ownership and board resolution.

- Establish DBA (e.g., 'AI AGENT CLG') or LLC subsidiary.

- Draft internal software governance policy. Deliverables:

- Board memo confirming alignment

- Registered DBA or LLC

- Updated IRS purpose (if required) Outcome: Secure legal structure for compliant tech development.

STEP TWO – Business Plan & Loan Package Objective: Create a professional funding package for SBA or CDFI lenders. Key Actions:

- Write a 5–7 page business plan

- Build a one-page MVP budget

- Draft a lender-ready cover letter

- Prepare 501(c)(3) letter, bank statements, and board endorsement Deliverables:

- Business plan

- Loan cover letter

- 1-page budget sheet

- SBA/CDFI checklist Outcome: Capital-ready package to raise $35,000–$50,000 in early funding.

STEP THREE – Brand Identity (AI AGENT CLG) Objective: Create a trusted, authoritative brand. Key Actions:

- Finalize name: AI AGENT CLG (Compliance and Licensing Group)

- Design logo: shield + digital circuit + embedded checkmark

- Choose palette: calming blue/green; clinical but friendly

- Tagline shortlist:

  - 'Your AI Guardian for Licensing and Accreditation.'

  - 'Compliance That Thinks.'

  - 'From Licensing to Accreditation – Fully Automated.'

- Secure domain (e.g., CLGagent.org) Deliverables:

- Logo design files (uploaded)

- Brand tagline sheet

- 1-page mission-aligned brand story Outcome: Clear, memorable identity for outreach, grant writing, and customer trust.

STEP FOUR – MVP Build Phase I: Facility Profile System Objective: Build a structured facility data engine. Key Actions:

- Design schema for each facility (name, license, ASAM level, staff, rooms, etc.)

- Build UI for admin data entry

- Link all outputs to profile engine

- Enable document previews and export Deliverables:

- Profile schema

- Admin UI

- Output generator

- Sample facility output PDF Outcome: Centralized data powers every future AI output.

STEP FIVE – MVP Build Phase II: Compliance AI Engine Objective: Automate generation of documents across DHCS and Joint Commission domains. Key Actions:

- Train models on Title 9, Joint Commission, ASAM, MAT, and IMS requirements

- Generate DHCS packets (e.g., 6001, 4022), P&Ps, logs, checklists

- Simulate audits, flag issues, suggest fixes Deliverables:

- AI agent

- Full licensing packet templates

- 15+ policy templates

- Log generator

- QA validation engine Outcome: Audit-proof, real-time documentation tailored to each facility.

STEP SIX – Pilot Facility Launch Objective: Test system in 2–3 real licensed facilities. Key Actions:

- Choose pilot partners (Detox, Res, OP)

- Input full profiles

- Deploy AI to generate full compliance suite

- Track staff time saved, accuracy, survey readiness Deliverables:

- Pilot usage data

- Pre/post compliance metrics

- Facility quotes & testimonials

- Final case study PDF Outcome: Real-world proof of value for investors and grants.

STEP SEVEN – Grant & Investor Materials Objective: Fund scale via grants and aligned investors. Key Actions:

- Write 1-page grant narrative

- Build pitch deck

- Target DHCS, Google.org, Microsoft AI for Good, SAMHSA

- Build submission toolkit: LOI, letters, budget, email outreach kit Deliverables:

- Grant narrative

- 5-slide deck

- Budget sheet for Phase II

- Outreach script + funding calendar Outcome: Capital sources secured to fund growth.

STEP EIGHT – Go Live & Scale Objective: Launch AI AGENT CLG as a live SaaS product. Key Actions:

- Finalize website, trial signup

- Define pricing tiers

- Launch onboarding flow + help desk

- Market via email, conferences, partner networks

- Continue iteration with feedback loop Deliverables:

- Live portal + trial accounts

- Tiered pricing page

- Marketing automation

- Compliance update system Outcome: AI AGENT CLG becomes the default operating system for healthcare licensing and survey compliance.